## Sheet1
My Tasks | Name | Start Date | End Date
Create Base UI For Login Page | seb | 2023-03-27 | 2023-03-27
Create User Class | seb | 2023-03-27 | 2023-03-27
Create UserManager Class | seb | 2023-03-27 | 2023-03-27
Revisit LoginPage UI - Add Logic for page, refine visual elements | seb | 2023-03-30 | 2023-04-03
Create class for User data persistence | seb | 2023-04-07 | 2023-04-12
Create Base UI for HomePage | seb | 2023-04-11 | 2023-04-11
Create updated diagrams | seb | 2023-04-12 | 2023-04-14
Create Project report | seb | 2023-04-12 | 2023-04-14
Create NutritionTracker Class | seb | 2023-04-12 | 2023-04-13
Create NutritionManager Class | seb | 2023-04-12 | 2023-04-13
Revise UserMainPageUI - Add logic for page. | seb | 2023-04-13 | 2023-04-13
Created Exercises Class | Kunal | 2023-03-20 | 2023-03-22
Created Workout class | Kunal | 2023-03-20 | 2023-03-22
Created Difficulty level enum | Kunal | 2023-03-20 | 2023-03-22
Created Add workout page | Kunal | 2023-03-29 | 2023-04-10
Created and Finalized styles and UI for all pages | Kunal | 2023-03-30 | 2023-04-14
Created My Plan Page | Kunal | 2023-04-10 | 2023-04-12
Created WorkoutJsonReader | Kunal | 2023-04-10 | 2023-04-12
Created WorkoutPlanJsonReader | Kunal | 2023-04-13 | 2023-04-14
Created and Updated Diagrams | Kunal | 2023-04-13 | 2023-04-14
Created IWorkoutmanager | Kunal | 2023-04-13 | 2023-04-14